## RA 01 (hidden)
M/S MECH ENGINEERS
Client : M/s Goa Natural Gas Pvt. Ltd.
Consultant : VCS Quality Services Pvt. Ltd.
GA: North Goa
RATE CONTRACT FOR LAYING ,ABOVE GROUND GI INSTALLATIONS INCLUDING LAST MILE CONNECTIVITY & DIRECT MARKETING SERVICES AT NORTH GOA - GA
ITEM NO. | DESCRPTION |  |  | UNIT | SOR AMOUNT | UNIT RATE | QTY | RA- 01 |  | RA- 02 |  | Balance Qty
PART - I : PE SECTION | [7 empty] | Qty | Amount | Qty | Amount
PL000.01.00 | MDPE pipeline laying in all type of surface ,using any laying methodology(Excluding HDD for 90 mm &125 mm);Clear cover to pipeline min 1.0 m;(Refer Drg No 1007-10-03-27)
PL000.01.01 | 20 mm Dia & 32 MM | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 2251468.8 | 446.72 | 8400 | 482.6 | 129352.2432 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 1125734.4 | 446.72 | 8400 | 104.1 | 13951.0656 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 375244.8 | 446.72 | 8400 |  | 0 |  | 0
PL000.01.02 | 63 mm Dia | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 809121.6 | 481.62 | 2800 | 1015.8 | 293537.7576 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 404560.8 | 481.62 | 2800 | 245.5 | 35471.313 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 134853.6 | 481.62 | 2800 |  | 0 |  | 0
PL000.01.03 | 90 mm Dia | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 938112 | 558.4 | 2800 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 469056 | 558.4 | 2800 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 156352 | 558.4 | 2800 |  | 0 |  | 0
PL000.01.04 | 125 mm Dia | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 301536 | 628.2 | 800 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 150768 | 628.2 | 800 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 50256 | 628.2 | 800 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
PL000.02.00 | MDPE pipeline laying by HDD Method ,with or without casing (Including supply & Installation of HDPE casing pipes) |  |  |  | 0 |  |  |  | 0 |  | 0
PL000.02.01 | Laying of 63 mm /90 mm Dia Mdpe by HDD method in all type of soil strata including hard rock strata without casing. | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 810796.8 | 1689.16 | 800 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 405398.4 | 1689.16 | 800 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 135132.8 | 1689.16 | 800 |  | 0 |  | 0
PL000.02.02 | laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 1661798.4 | 1731.04 | 1600 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 830899.2 | 1731.04 | 1600 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 276966.4 | 1731.04 | 1600 |  | 0 |  | 0
PL000.02.03 | Laying of 63 mm /90 mm Dia Mdpe by HDD method in all type of soil strata including hard rock strata with casing. | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 107547.84 | 2240.58 | 80 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 53773.92 | 2240.58 | 80 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 17924.64 | 2240.58 | 80 |  | 0 |  | 0
PL000.02.04 | laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | completion of laying work in continuous stretches of minimum 500mtrs.Including jointing of pipeline, backfilling and compaction for the complete stretch as per scope of work and on submission of DPR/WPR and graphs. | 60% | M | 109558.08 | 2282.46 | 80 |  | 0 |  | 0
|  | testing of completed network and submission of “As Built, As Graph Drawings”subject to installation of PE Stop Off Valve and permanent markers in the network area & On completion of 80% service line/taping as per duly singed & approved survey of laid network. | 30% | M | 54779.04 | 2282.46 | 80 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract & reconciliation of material. | 10% | M | 18259.68 | 2282.46 | 80 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
| Commissioning of already pressure tested and N2 Purged MDPE pipeline (from 20 mm to 125 mm). | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 327166.56 | 20.94 | 17360 | 59.8 | 1126.9908 | 289.8 | 5461.5708
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 36351.84 | 20.94 | 17360 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
PL000.03.00 | Excavation of hard rock |  |  |  | 0 |  |  |  | 0 |  | 0
PL000.03.01 | Excavation of hard rock | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | cum | 334202.4 | 928.34 | 400 | 84.664 | 70737.28 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | cum | 37133.6 | 928.34 | 400 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
PL000.04.00 | Fabrication & Installation of Pipeline Markers : |  |  |  | 0 |  |  |  | 0 |  | 0
PL000.04.01 | RCC route Markers as per Drg No 1007-10-03--29 as per instruction of EIC and specifications. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 93224.88 | 369.94 | 280 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 10358.32 | 369.94 | 280 |  | 0 |  | 0
PL000.04.02 | Pole Markers with foundation as per Drawing No Drg No 1007-10-03-30 & 1007-10-03-31 and instructions of EIC and Specification. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 132675.84 | 1535.6 | 96 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 14741.76 | 1535.6 | 96 |  | 0 |  | 0
PL000.04.03 | Plate marker as per Drg No 1007-10-03--28 at house as per instruction of EIC and specifications. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 301536 | 209.4 | 1600 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 33504 | 209.4 | 1600 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
PL000.05.00 | Charges of compliance to health ,Safety & Environment (HSE) as detailed in scope of work. |  |  |  | 0 |  |  |  | 0 |  | 0
PL000.05.01 | MDPE Section | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Mtrs | 87948 | 6.98 | 14000 | 1498.4 | 9412.9488 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Mtrs | 9772 | 6.98 | 14000 |  | 0 |  | 0
PL000.05.02 | GI Section- Upto 4th GI (G+4) | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 52768.8 | 146.58 | 400 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 5863.2 | 146.58 | 400 |  | 0 |  | 0
PL000.05.03 | GI Section- GI (G+5) and above including high rise Above 4th floor | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 12061.44 | 167.52 | 80 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 1340.16 | 167.52 | 80 |  | 0 |  | 0
PART II : GI/COPPER SECTION | [8 empty] | 0 |  | 0
PL000.06.00 | Supply & Installation of powder coated GI Pipe & Fittings | [7 empty] | 0 |  | 0
| NON LMC | [7 empty] | 0 |  | 0
PL000.06.01 | Supply and installation powder coated 1/2"GI pipe from TF to Regulator isolation valve including TF of required size. | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | Nos | 1031923.2 | 537.46 | 2400 |  | 0 | 17 | 7309.456
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | Nos | 128990.4 | 537.46 | 2400 |  | 0 | 17 | 913.682
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | Nos | 128990.4 | 537.46 | 2400 |  | 0 |  | 0
PL000.06.02 | Supply & installation of powder coated 1/2 " GI pipe from regulator isolation valve up to G + 4 Apt and individual Kothi/Bunglow.Refer Drf No: 1007-10-03-02 | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | M | 7594240 | 593.3 | 16000 |  | 0 | 781.1 | 370741.304
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | M | 949280 | 593.3 | 16000 |  | 0 | 781.1 | 46342.663
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | M | 949280 | 593.3 | 16000 |  | 0 |  | 0
PL000.06.03 | Supply and installation powder coated 3/4" Gipipe from TF to regulator isolation valve including TF of required size | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | Nos | 33504 | 698 | 60 |  | 0 |  | 0
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | Nos | 4188 | 698 | 60 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | Nos | 4188 | 698 | 60 |  | 0 |  | 0
PL000.06.04 | Supply and installation powder coated 3/4" Gipipe from TF to regulator isolation valve to lateral isolation valve above G + 4 Apt and individual Kothi/Bunglow.Refer Drf No: 1007-10-03-02 | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | M | 1353561.6 | 704.98 | 2400 |  | 0 | 230.15 | 129800.9176
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | M | 169195.2 | 704.98 | 2400 |  | 0 | 230.15 | 16225.1147
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | M | 169195.2 | 704.98 | 2400 |  | 0 |  | 0
PL000.06.05 | Supply and installation powder coated 1"from TF to regulator isolation valve including TF of required size | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | Nos | 13401.6 | 837.6 | 20 |  | 0 |  | 0
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | Nos | 1675.2 | 837.6 | 20 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | Nos | 1675.2 | 837.6 | 20 |  | 0 |  | 0
PL000.06.06 | Supply and installation powder coated 1" Gipipe from TF to regulator isolation valve to lateral isolation valve above G + 4 Apt and individual Kothi/Bunglow.Refer Drf No: 1007-10-03-02 | installation of GI / Copper pipes including all fittings, regulators, valves, clamping, cementing of holes, painting and testing of installation and material consumption booking and updation of meter no. against BP in CRM/SAP | 80% | M | 135132.8 | 844.58 | 200 |  | 0 |  | 0
|  | after testing and commissioning of GI, copper installation on gas & submission of RFC card. | 10% | M | 16891.6 | 844.58 | 200 |  | 0 |  | 0
|  | purchase / work order closure and submission of all documents as per contract and reconciliation of GNGPL issued material. | 10% | M | 16891.6 | 844.58 | 200 |  | 0 |  | 0
[9 empty] | 0 |  | 0
| Commissioning of already pressure Tested GI Pipe /Riser (1/2",3/4" and 1") | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 1168452 | 69.8 | 18600 |  | 0 | 409.85 | 25746.777
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 129828 | 69.8 | 18600 |  | 0 |  | 0
[9 empty] | 0 |  | 0
PL000.07.00 | LAST MILE CONNECTIVITY(LMC) | [7 empty] | 0 |  | 0
PL000.07.01 | LMC- PNG CONNECTIONS IN PROJECT AREA | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 417124.8 | 1158.68 | 400 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 46347.2 | 1158.68 | 400 |  | 0 |  | 0
PL000.07.02 | LMC-PNG CONNECTIONS IN O & M AREA (ON EXISTING RISER) | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 909633.6 | 1263.38 | 800 | 2 | 2274.084 | 17 | 19329.714
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 101070.4 | 1263.38 | 800 |  | 0 |  | 0
[9 empty] | 0 |  | 0
PL000.08.00 | Powder coated GI and Cu Installation for pipes more than 4m per connection | [7 empty] | 0 |  | 0
PL000.08.01 | 1/2" powder coated GI | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 1394604 | 258.26 | 6000 | 4.4 | 1022.7096 | 20.2 | 4695.1668
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 154956 | 258.26 | 6000 |  | 0 |  | 0
PL000.08.02 | 12 mm copper pipe | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 502560 | 279.2 | 2000 | 3.1 | 778.968 | 23.8 | 5980.464
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 55840 | 279.2 | 2000 |  | 0 |  | 0
[9 empty] | 0 |  | 0
PL000.09.00 | Testing and conversion of domestic appliances in projest & O & M areas: | [7 empty] | 0 |  | 0
PL000.09.01 | Testing and conversion of Domestic Appliances in O & M area : (NG conversion per connection) | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | NOS | 110563.2 | 153.56 | 800 | 39 | 5389.956 | 17 | 2349.468
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | NOS | 12284.8 | 153.56 | 800 |  | 0 |  | 0
Part - III : Civil works | [8 empty] | 0 |  | 0
CV001.00.00 | Equipment foundation Works : (Excavation ,Providing and Laying Reinforced Cement Concrete (M - 20) | [7 empty] | 0 |  | 0
CV001.01.00 | Equipment foundation Works : (Excavation ,Providing and Laying Reinforced Cement Concrete (M - 20) | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | CU.M. | 216100.8 | 6002.8 | 40 | 2.59 | 13992.5268 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | CU.M. | 24011.2 | 6002.8 | 40 |  | 0 |  | 0
| Supply and placing in position high strength deformed steel bars reinforcement (conforming to IS: 1786, Grade Fe 415) | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | KG | 71614.8 | 66.31 | 1200 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | KG | 7957.2 | 66.31 | 1200 |  | 0 |  | 0
[9 empty] | 0 |  | 0
CV002.00.00 | Installations of DRS/DCU/MRS/Metering Skid/service regulator | [7 empty] | 0 |  | 0
CV002.01.00 | DRS/DCU | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | NOS | 50256 | 27920 | 2 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | NOS | 5584 | 27920 | 2 |  | 0 |  | 0
Cv002.02.00 | MRS / Metering Skids Providing, | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | NOS | 314100 | 43625 | 8 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | NOS | 34900 | 43625 | 8 |  | 0 |  | 0
CV002.03.00 | Installation of Service regulator with canopy including all fittings with civil works | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 135691.2 | 6282 | 24 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 15076.8 | 6282 | 24 |  | 0 |  | 0
[9 empty] | 0 |  | 0
CV003.00.00 | Installation of vale chambers : | [7 empty] | 0 |  | 0
CV003.02.00 | RCC valve Chamber -size (LxW) - 1m x1m | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 124383.6 | 23034 | 6 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 13820.4 | 23034 | 6 |  | 0 |  | 0
CV003.03.00 | RCC valve Chamber -size (LxW) - 1.5 m x1m | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 184690.8 | 34202 | 6 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 20521.2 | 34202 | 6 |  | 0 |  | 0
CV003.04.00 | Brick valve Chamber -size (LxW) - 1m x1m | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 31033.08 | 17240.6 | 2 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 3448.12 | 17240.6 | 2 |  | 0 |  | 0
CV003.05.00 | Brick valve Chamber -size (LxW) - 1.5 m x1m | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 46486.8 | 25826 | 2 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 5165.2 | 25826 | 2 |  | 0 |  | 0
Part - IV (Marketing ) DMA | [8 empty] | 0 |  | 0
DM001.01.00 | Domestic PNG connections | the number of commercial / industrial registrations made, evaluation and facilitation of signing of GSA with customer along with collection of security deposit amount by DMA and realization of collected amount in GNGPL bank account duly certified by Engineer-in-Charge (EIC). | 95% | Nos | 206887.2 | 181.48 | 1200 |  | 0 |  | 0
|  | contract closure and submission of all documents as per contract. | 5% | Nos | 10888.8 | 181.48 | 1200 |  | 0 |  | 0
DM001.02.00 | Commercial PNG connections | the number of commercial / industrial registrations made, evaluation and facilitation of signing of GSA with customer along with collection of security deposit amount by DMA and realization of collected amount in GNGPL bank account duly certified by Engineer-in-Charge (EIC). | 95% | Nos | 5039.56 | 1326.2 | 4 |  | 0 |  | 0
|  | contract closure and submission of all documents as per contract. | 5% | Nos | 265.24 | 1326.2 | 4 |  | 0 |  | 0
PART -V (PENDING MDPE/LMC WORK DONE BY OTHER CONTRACTORS & FABRICATION JOB | [8 empty] | 0 |  | 0
A | LMC SECTION (GI) | [7 empty] | 0 |  | 0
A.01.01 | Charges for testing and commissioning of GI Riser work done by other contractor 1/2" , 3/4", 1" | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 251280 | 27.92 | 10000 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 27920 | 27.92 | 10000 |  | 0 |  | 0
B | MDPE SECTION | [7 empty] | 0 |  | 0
B.01.00 | Charges for rectification /Hookup of existing networks (Including all fittings),testing & commissioning MDPE network. | [7 empty] | 0 |  | 0
B.01.01 | Charges for testing and commissioning of MDPE work done by other contractor upto Dia 63 mm. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 201024 | 55.84 | 4000 |  | 0 | 81.2 | 4080.7872
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 22336 | 55.84 | 4000 |  | 0 |  | 0
B.01.02 | Charges for testing and commissioning of MDPE work done by other contractor above Dia 63 mm. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 226152 | 62.82 | 4000 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 25128 | 62.82 | 4000 |  | 0 |  | 0
[9 empty] | 0 |  | 0
B.02.00 | RESTORATION | [7 empty] | 0 |  | 0
B.02.01 | Restoration of Asphalted /Bituminous road | after completion of restoration and certification by consultants / Third Party Inspection agency nominated by GNGPL. | 80% | RM | 1116800 | 349 | 4000 |  | 0 |  | 0
|  | after obtaining NOC from respective local authorities / Third party agencies designated by land owning agencies / Resident Welfare Associations etc. | 10% | RM | 139600 | 349 | 4000 |  | 0 |  | 0
|  | after completion of all works and closure of purchase / work order. | 10% | RM | 139600 | 349 | 4000 |  | 0 |  | 0
B.02.02 | Restoration of concrete pavement ,Agra/kota stone ?Tiles (Chequered/ointerlocking etc.). | after completion of restoration and certification by consultants / Third Party Inspection agency nominated by GNGPL. | 80% | RM | 1366963.2 | 355.98 | 4800 |  | 0 |  | 0
|  | after obtaining NOC from respective local authorities / Third party agencies designated by land owning agencies / Resident Welfare Associations etc. | 10% | RM | 170870.4 | 355.98 | 4800 |  | 0 |  | 0
|  | after completion of all works and closure of purchase / work order. | 10% | RM | 170870.4 | 355.98 | 4800 |  | 0 |  | 0
B.02.03 | Restoration pf Plain cement Concrete (PCC) | after completion of restoration and certification by consultants / Third Party Inspection agency nominated by GNGPL. | 80% | RM | 670080 | 418.8 | 2000 |  | 0 |  | 0
|  | after obtaining NOC from respective local authorities / Third party agencies designated by land owning agencies / Resident Welfare Associations etc. | 10% | RM | 83760 | 418.8 | 2000 |  | 0 |  | 0
|  | after completion of all works and closure of purchase / work order. | 10% | RM | 83760 | 418.8 | 2000 |  | 0 |  | 0
B.02.04 | Restoration of Dry Brick pavement | after completion of restoration and certification by consultants / Third Party Inspection agency nominated by GNGPL. | 80% | RM | 402048 | 251.28 | 2000 | 51.9 | 10433.1456 |  | 0
|  | after obtaining NOC from respective local authorities / Third party agencies designated by land owning agencies / Resident Welfare Associations etc. | 10% | RM | 50256 | 251.28 | 2000 |  | 0 |  | 0
|  | after completion of all works and closure of purchase / work order. | 10% | RM | 50256 | 251.28 | 2000 |  | 0 |  | 0
[9 empty] | 0 |  | 0
B.03.00 | LIASION | [7 empty] | 0 |  | 0
B.03.01 | Liasion with authorities like NHAI ,railway ,PWD etc. and getting permission for laying of MDPE pipeline .Payment shall be made only if permission is received from authority. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | M | 552816 | 153.56 | 4000 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | M | 61424 | 153.56 | 4000 |  | 0 |  | 0
B.03.02 | Liasion with local authority during the construction work and payment shall mbe made as per actual length of pipe laid. | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | RM | 603072 | 55.84 | 12000 | 1498.4 | 75303.5904 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | RM | 67008 | 55.84 | 12000 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
B.04.00 | MDPE Service line laying in old Projects /O & M areas | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 321638.4 | 1786.88 | 200 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 35737.6 | 1786.88 | 200 |  | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 |  | 0
C.01.00 | COMMERCIAL/NON DOMESTIC CONNECTION | Progressively on completion of individual item work on pro-rata basis as certified in monthly progress bill. | 90% | Nos | 276408 | 6980 | 44 |  | 0 |  | 0
|  | Completion of all works in all respects and acceptance thereof by Engineer-in- Charge. | 10% | Nos | 30712 | 6980 | 44 |  | 0 |  | 0
BASIC AMOUNT | [8 empty] | 662784.5794 |  | 638977.0851
GST AMOUNT ( 18%) | [8 empty] | 119301.2243 |  | 115015.8753
TOTAL AMOUNT | [8 empty] | 782085.8037 |  | 753992.9604

## revised rate (hidden)
SCHEDULE OF RATES (SOR) RATE CONTRACT FOR MDPE LAYING, ABOVEGROUND GI INSTALLATIONS INCLUDING LAST MILE CONNECTIVITY & DIRECT MARKETING SERVICES AT NORTH GOA-GA Tender No.:
Item NO. |  | Unit | Quantity | Unit Rate |  |  |  | 10% over head
1 | [18 empty] | For HDD
PART-I : PE SECTION | [18 empty] | 20% | Calculated Rate |  | Adopted Rate
A | Route survey of allotted areas and Preparation /Submission of detailed route plan for approval by EIC in AutoCAD format. Receiving, handling, loading, transportation and unloading of owner supplied MDPE pipes and other free issue items from GNGPL's designated stock yards to Contractor's own stock-yards/ work-sites. Proper storing, stacking, identification, providing security and insurance cover for the materials. Procurement / Supply and Installation of PE Fittings, PE Valves, Transition Fittings, Warning Mats, HDPE casing Pipes, Half concrete sleeves and all other items required for execution shall also be in Contractor's scope. Liaisoning with Landowning agencies / statutory authorities and obtaining permission from them making trial pits to determine the underground utilities/ services etc., restoration of the abandoned excavation/ trial pits (excavated to depth of 1.5 m or more as per satisfaction to EIC) to original condition, barricading the work area as per the procedures & drawings provided in the tender and as per the directions of EIC / Site-in-charge; uncoiling / stringing of pipes, jointing of the pipe ends/ fittings (Isolation Valve 1/2" & 3/4") / Transition fittings/ valves by qualified personnel, using approved electro fusion techniques as per specification. Installation of PE Valve shall be done as per PNGRB guideline and Instructions of EIC.
Trenching of normal soil / Morrum (red soil)/ Malva / Multiple layer of Bitumen road, hard rock/ boulders using manual/pneumatic chisel and disposal of excess soil/boulders/rock etc. is in the scope of contractor and the same is to be considered by the contractor.
Surveying of route and detours required at the time of execution,preparation of construction drawings showing survey details and submit same to GNGPL/PMC for review/approval.
Submission of applications as per approved drawings provided by owner / owner's representative (Initial Route Survey, Preperation of Drawings, measuring and providing details of surface type shall be in scope of Contractor with approval from Owner / Owner's representative), obtaining & submission of demand note, Coordination, Liaisoning, Obtaining written permissions from Land owing agencies like private road/ apartment road, municipal corporations, PWD, NHAI, AAI, Forest Dept., Indian Railways and any other government/ private agencies who maintains the public lands. including liasioning during execution of work and obtaining NOC from the applicable authorities. NOte :SOR 3.000 PART V TO BE REFERRED.
Compliance to TS4,construction safety of MDPE Section-PPE, Continuous hard Barricades along the trenches as per approved drawing in tender, Use of Gum Boots, Hand gloves, Reflective jackets, Hard hats (helmets), Safety shoes, eye and ear safety equipment's, Fire extinguishers and as per the detailed scope of work in tender specifications.
Laying using any method (Open trench & Moling/ HDD) with or without casing; it includes survey of the under ground utilities, execution of the work as per specification (as per trench dimension Drg -attached in tender), including excavation of pits, moling with hole size not exceeding 20% of the the carrier / casing pipe dia. jointing and insertion of the carrier pipe in casing pipe (on case to case basis) and subsequent padding with soft soil, laying of warning mat in open trench only, backfilling, compaction, submission of as built drawing, as graphs as per attached specification and instruction of ElC / Site Engineer of Owner. Includes laying of pipeline in all type of surface including Kutcha, metal, concrete (PCC/RCC), bituminous, tiled, brick lined etc. after raking up of hard surface of any type; Roads, Pavement, Footpaths etc. shall be made motorable once the pipeline is laid.
All service line as required shall be laid within this SOR and no extra payment shall be made for service line in any other SOR line item.
Supply & installation of Gl Sleeves, 2.5" NB x 300 mm length GI pipe Sleeve / Half Round Concrete Sleeves for domestic connections, 3" NB x 300 mm length Gl Sleeve for commercial and industrial installations (as per GI Pipe Sleeve Drg No 1007-10-03--18), and 1/2 Round concrete sleeve, Drg No 1007- 10-03--33) excavation, breaking through any obstructions, insertion of pipe, sealing the annulus, fixing of the sleeves with concrete mix, preparation of pedestal & restoration of excavated pits within the size of pedestal & the same pit with the laying of 20/32 mm dia MDPE pipe as defined in technical specification and instruction of ElC.
Restoration to original conditions of dismantled surface like Asphalted/Bituminous Road, Concrete Pavement, Agra /Kota Stones / Tiles (Chequered/interlocking etc.), Dry Brick Pavement as per the technical specifications attached in the tender after laying of pipeline in Built- Up surface, as per the directions of EIC / Site lncharge. Scope includes supply of the approved quality material, testing of materials by third party agencies as per technical specification / CPWD / IRC Standards, submission of the restoration reports, obtaining no objection certificates from the concern local authorities /land owners / third party inspection agencies designated by land owing agencies and Owner. Note: SOR 2.000 PART V TO BE REFERRED.
Flushing, cleaning ,Pneumatic testing, purging with nitrogen and commissioning as per specification and approved procedures providing all tools and tackles, nitrogen, instruments, manpower and other related accessories including PPE and as per instructions of the Engineer-in charge.
Maintaining the completed pipelines/ installation for any defect, failures during defect liability period.
Handing over the completed works to GNGPL for their operation/ use, returning of all surplus material to GNGPL stores, reconciliation of free issue material area wise and obtaining no objection certificate.
On completion of gas charging of pipelines, preparation and submission of As built drawings, As graph drawings, crossings details, termination, utility graphs and deviation statements with Hard & Soft copy.
Submission of all documents required for contract closure in numbers as mentioned in contract.
GPS Co-ordinate to be taken of laid PE pipeline and GPS instrument to be in Contractors scope.
Laying of MDPE pipeline, with or without casing, in case if existing dedicated trench of approx. size 400mm x 600mm is already provided with removable top cover; Scope includes removal of precast RCC slab covers from channel, laying of pipeline, jointing, testing, sand filling (including supply) refixing top cover of pipe trench.
In case 2 MDPE pipelines are laid in a common trench, SOR rate of higher dia plus 1/3 (0.333) x SOR rate of lower dia will be paid
Note: Supply & Installation of GI Sleeve 1/2 round concrete sleeve & warning mat (Open trench excavation) shall be included in laying of MDPE Pipe.
Any other activities not mentioned / covered explicitly above, but otherwise required for satisfactory completion / operation / safety / statutory / maintenance of the works shall also be covered under the scope of work and has to be completed by Contractor within specified schedule at no extra cost to Owner. All the work shall be executed in accordance with the provision of contract. Commissioning or Gas Charging of MDPE pipeline of any size shall be paid as per seperate SOR Item mentioned.
A.0.00 | MDPE Pipe line laying in all type of surface, (Katcha surface/ Normal Surface/Hard surface) by Trenching Method
A.0.01 | 20 mm Dia | M | 2000 | 446.72 | 893440 |  |  | 491.392 | 982784 | [9 empty] | 0 | 0 |  | 0
A.0.02 | 32 mm Dia | M | 8848 | 460 | 4070080 | 100 |  | 506 | 4477088
A.0.03 | 63 mm Dia | M | 8500 | 481.62 | 4093770 | 170 |  | 529.782 | 4503147 | [9 empty] | 34 | 204 |  | 200
A.0.04 | 90 mm Dia | M | 3000 | 558.4 | 1675200 | 60 |  | 614.24 | 1842720 | [10 empty] | 60 |  | 60
A.0.05 | 125 mm Dia | M | 2000 | 628.2 | 1256400 | 40 |  | 691.02 | 1382040 | [10 empty] | 40 |  | 40
A.1.00 | MDPE Pipe line laying by HDD Method, with or Without casing (Including supply & installation of HDPE Casing Pipes) |  |  |  | 0 |  |  | 0 | 0
| Survey of the under ground utilities, submission of HDD profile for approval (excluding road and nala crossings), execution of the work as per the standard procedure attached, including excavation of the pits, Jointing of casing and carrier pipe and insertion of the carrier pipe in casing of dia ranging from 120mm to 180mm for 90 mm & 200mm to 250 mm dia for 125 mm dia MDPE , subsequent sealing, backfilling, compaction, submission of as built graphs, final HDD profiles as per attached specification and the instruction of EIC / Site Engineer of Owner. The other activities are as per SOR Item No. I and as detailed in specification and as per the instructions of the EIC / Site engineer of Owner. The supply of casing pipe shall bein the scope of contractor. The payment shall be made for length of casing pipe laid in HDD, remaining carrier pipe length without casing shall be paid under SOR item no.1 Commissioning or Gas Charging of MDPE pipeline of any size shall be paid as per seperate SOR Item mentioned. |  |  |  | 0 |  |  | 0 | 0
A.1.01 | Laying of 63 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 3000 | 1858.076 | 5574228 | 60 |  | 2043.8836 | 6131650.8 | 2043.8836 | [9 empty] | #DIV/0! |  | #DIV/0!
A.1.02 | Laying of 90 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 6500 | 1870 | 12155000 | 130 |  | 2057 | 13370500 | 2057
A.1.03 | Laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 1000 | 1904.144 | 1904144 | 20 |  | 2094.5584 | 2094558.4 | 2094.5584 | [9 empty] | #DIV/0! |  | #DIV/0!
[5 empty] | 0 |  |  | 0 | 0
A.1.04 | Laying of 63 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2240.58 | 224058 | 2 |  | 2464.638 | 246463.8 | [10 empty] | #DIV/0! |  | #DIV/0!
A.1.05 | Laying of 90 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2260 | 226000 | 2 |  | 2486 | 248600
A.1.06 | Laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2282.46 | 228246 | 2 |  | 2510.706 | 251070.6 | [10 empty] | #DIV/0! |  | #DIV/0!
A.2.00 | Excavation of hard rock |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Trenching of Hard Rock is defined as trench material with a single piece of rock, dimension exceeding 1.0 meter in any direction, which requires cutting only by use of manual/pneumatic chisel/drill or sledge hammer and chisel or removal of same by additional techniques. The disposal of excess rock as per the requirement of authorities. The rates are payable over and above the Laying rates as per relevant SOR item no. - PL000.01.00. |  |  |  | 0 |  | 24000 | 0 | 0 | [12 empty] | 0
A.2.01 | Excavation of Hard Rock. | CUM | 500 | 1200 | 600000 |  |  | 1320 | 660000 | 1200 | [9 empty] | #DIV/0! |  | #DIV/0!
A.3.00 | Fabrication & Installation of Pipeline Markers: |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Supply and Installation of Stone Route Markers, Powder Coated Plate / Pole Markers as per the attached drawings, along the route / along boundary wall, lamp posts including all associated civil works such as excavation and construction in all types of soils, construction of pedestals of RCC and PCC and grouting with concrete, cleaning, supply and application of approved colour and quality of primer and paint, stencil letter cutting of numbers, direction, chainage etc., restoration of area to original condition and performing all works as per drawings, specification and instruction of Engineer-in-Charge. The rates shall include liaison rates with statutory bodies and restoration rates and no separate rates are payable under this SOR. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
A.3.01 | RCC Route Markers as per Drg No 1007-10-03--29 as per instruction of EIC and specifications. | Nos | 480 | 849 | 407520 |  | 160 | 933.9 | 448272 | 849 | From BGL | [8 empty] | 0 |  | 0
A.3.02 | Pole markers with foundation as per Drawing No. Drg No 1007-10-03-30 & 1007-10-03-31 and instructions of EIC and specification | Nos | 160 | 3183 | 509280 |  |  | 3501.3 | 560208 | 3183 | [9 empty] | #DIV/0! |  | #DIV/0!
A.3.03 | Plate marker as per Drg No Drg No 1007-10-03--28 at house as per instruction of EIC and specifications. | Nos | 500 | 582 | 291000 |  |  | 640.2 | 320100 | 582 | [9 empty] | #DIV/0! |  | #DIV/0!
PART II : GI / COPPER SECTION |  |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
B | Supply & Installation of Powder Coated GI Pipe & Fittings |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Assessment of material requirement for installation at site, Order placement and Purchasing of Powder coated Gl Pipes, GI fittings, Copper pipes & fittings, Brass Fittings, Isolation Valves & appliance valves from approved vendors of GNGPL, Scheduling, Planning of material & Forwarding inspection call, getting dispatch clearance, handling, loading, transportation and unloading of these items at respective contractor's store. Receiving, taking over, handling, loading, transportation and unloading of owner supplied above ground fittings such as regulators, meters and free issue items (if any other) as defined in specification from Owner's designated stock yards to Contractor's own stores / work sites, proper storing, stacking, identification, providing security and insurance cover. Preparation and approval of sketches, schedules & execution procedures. Finalising optimum route with consent of customer from transition fitting to cooking oven / appliance and ensuring installations in well ventilated area. Making temporary but stable platforms/ scaffolding/ rope ladders and supply of all other safety devices. Portal entry for new connections - New registration tracking and feasibility survey and its updation as per GNGPL defined TAT; printing of stationary as per approved GNGPL formats required during connections. Follow-up and attend complaints receives from customer regarding delay in new connection & NG conversion (ReferDrg No 1007-10-03-01, 02, 03) |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Installation of GI service pipes & fittings, regulators, Valves etc. including NPT threading, as specified, Drillings of holes through the walls (Brick, RCC), Granite, Marble, Wood Cutting, Glass Cutting with proper heavy duty hammer drill machine, tools & tackles, using proper sealant/ grout material and colours to match the original replacement of the damages during drilling, restoring the area to the original condition, Painting of scratched length of powder coated pipe and fittings after proper surface finish by one coat of approved primer paint and two coats of approved synthetic enamel paint. Restoring the wall surface to original conditions. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Copper tube shall be installed from the downstream of meter up to the isolation valve before the customer appliance as per requirement and the satisfaction of EIC, the contractor to provide all equipment, tools and materials necessary to execute the work in efficient manner by cutting, cleaning, flux application, soldering and lacquering. The work includes supply of tools, tackles and consumables including clamp for fixing the tubes. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Supply & fixing of approved clamps & nylon rawl plugs with SS-304, 2" screws, grout material, suitable thread sealant i.e. Teflon Tape, Joining of transition fitting to above ground service GI pipes, testing, purging and commission of the complete installation. The rates in connections also includes meter installation, tap off rates. The GI installation in already gas charged areas, planning & coordinating with existing consumer's for New tap offs from existing riser with or without tee, testing of these existing risers and commissioning of these connections with newly tapp offs etc.is inclusive. Payment against the commissioning of GI pipe shall be made as per seperate SOR mentioned. |  |  |  | 0 |  |  | 0 | 0 |  |  | VIJAY SALES CORPORATION PRICE LIST FOR JINDAL STAR W.E.F.: 11/03/2022 | Discount @ 40% | Fittings | Sum | Freight | OHPM |  | Quantity as communicated by PM (Jitender Sir) | Supply Rate | Installation Rate | #VALUE!
B.0.00 | GI Work |  |  |  | 0 |  |  | 0 | 0 |  |  | Supply | 40% | 30% |  | 5% | 10% |  | metre |  |  | 0
B.0.01 | Supply & Installation of powder coated 1/2" Gl Riser from TF to lateral isolation valve up to G+4 Apt and Individual kothi/ Bungalow. Refer Drg No.: 1007-10-03-02) | M | 8000 | 537.46 | 4299680 | 15000 |  | 591.206 | 4729648 |  |  | 264 | 188.5714 |  | 188.5714 | 9.4286 | 18.8571 | 216.8571 | 1.5 | 15325.2857 | 15000 | 30330
B.0.02 | Supply & Installation of powder coated 3/4" Gl Riser from TF to lateral isolation valve above G+4 Apt and Individual kothi/ Bungalow. Refer Drg No.: 1007-10-03-02) | M | 7000 | 698 | 4886000 |  |  | 767.8 | 5374600 |  |  | 332 | 237.1429 |  | 237.1429 | 11.8571 | 23.7143 | 272.7143 | 1.5 | 409.0714 | 0 | 410
B.0.03 | Supply & Installation of powder coated 1" Gl Riser from TF to lateral isolation valve above G+4 Apt and Individual kothi/ Bungalow. Refer Drg No.: 1007-10-03-02) | M | 2500 | 837.6 | 2094000 |  |  | 921.36 | 2303400 |  |  | 499 | 356.4286 |  | 356.4286 | 17.8214 | 35.6429 | 409.8929 | 1.5 | 614.8393 | 0 | 610
B.1.00 | METER INSTALLATION |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
B.1.01 | PNG CONNECTIONS IN PROJECT AREA |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Supply and installation from lateral isolation valve to appliance along with meter installation - The cumulative length of 1/2 "GI within 2 m & Cu within 2m or (GI + Cu) within 4m after lateral isolation valve up to appliance along with installation of meter, supply of rubber hose with clamps and conversion of burner . Additional quantity above 4 Meters (GI + Cu) shall be payable only in case cumulative length exceeds 4 m. Payment against additional length of (GI / Cu) shall be as per item 8 of SOR. | Nos | 4000 | 2938.87 | 11755480 | 2000 |  | 3232.757 | 12931028 | 2938.87 | From IGL | [8 empty] | 2000 |  | 2000
B.1.02 | PNG CONNECTIONS IN O&M AREA (ON EXISTING RISER OR GASIFIDE AREA) |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Supply and installation from existing riser to appliance along with meter installation - Supply and installation from lateral isolation valve to appliance along with meter installation, supply of rubber hose with clamps and conversion of burners- The cumulative length of 1/2 "GI within 2 m & Cu within 2m or (GI + Cu) within 4m after lateral isolation valve up to appliance along with installation of meter . Additional quantity above 4 Meters (GI + Cu) shall be payable only in case cumulative length exceeds 4 m. Payment against additional length of (GI / Cu) shall be as per item 8 of SOR. | Nos | 3000 | 3498.48 | 10495440 | 1500 |  | 3848.328 | 11544984 | 3498.48 | [9 empty] | 1500 |  | 1500
B.2.00 | Cu installations for pipes more than 2 m per connection |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
B.2.01 | 12 mm Copper Pipe | M | 3000 | 279.2 | 837600 |  |  | 307.12 | 921360 | [10 empty] | 0 |  | 0
LMC | Note: 1. GI, Cu, brass fittings shall not be counted separately. It shall be measured along with GI & Cu pipe. 2. If Cumulative length of GI & Cu increases specified lengths in connection rate SOR no. PL000.07.01 and PL000.07.02, extra piping shall be paid considering installation as done in Flats or bungalows as per SOR item no.: PL000.08.00. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
B.3.00 | Testing and conversion of Domestic Appliances in Project & O&M area: |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Conversions of all types of LPG Kitchen appliances to NG based appliances, Supply & changing of the nozzles / jets and associated controls for domestic & imported appliances with proper tools and tackles. The rates include testing of Kitchen piping from meter to Appliance valve and supply and fixing of one steel reinforced rubber hose (1.5 m) per appliance/stove with clamps. Cleaning and performing minor maintenance, greasing etc. of the appliance. Testing and showing the performance to the customer, signing of joint meter records (JMR) and instructing the customer on use & safety norms, complete as per specifications & to satisfaction of owner / Engineer in Charge. This SOR is applicable for left out NG conversions by other contractor or as per the instructions of EIC. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
B.3.01 | Testing and conversion of Domestic Appliances in Project and O&M area: (NG Conversion per Connection) | Nos | 8000 | 293 | 2344000 |  |  | 322.3 | 2578400 | 293 | From IGL | [8 empty] | 0 |  | 0
B.4.00 | COMMERCIAL/NON DOMESTIC CONNECTION |  |  |  | 0 |  |  | 0 | 0
B.4.01 | Installation of gas meter,regulator, supply and installation of meter inlet pipe Welded ( Electrical Resistance Welded (ERW) Galvanized Iron (GI) pipes of Heavy class ). Scope of work under pertaining to Commercial /Non Domestic connections . Scope includes Supply and installation of box / enclosure/Meter Bracket (for Gas meter and regulator ), Strainer & Meter Connector . Supply and installation of safety sign boards as per ‘Technical requirements . This SOR is for meter fixation with riser regulator. | Nos | 50 | 6980 | 349000 |  |  | 7678 | 383900
[5 empty] | 0 |  |  | 0 | 0
PART -III : Civil Works |  |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
C.0.00 | Equipment Foundation works: (Excavation, Providing and Laying Reinforced Cement Concrete (M-20) |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
C.0.01 | Excavation in any plane & dimension including disposal of excavated earth up to any lead in all conditions, backfilling using serviceable earth and disposal of surplus and unserviceable earth. Soil to be levelled and properly compacted complete in all respect as per scope of work, technical specification and directions of EIC. Providing and laying REINFORCED CEMENT CONCRETE OF M-20 Grade (Concrete shall be design mix / nominal mix) with 20mm & down size graded crushed stone aggregates in NON SUSPENDED slabs/pavement slabs including pedestals, ramps etc., laying in alternate panels to required slopes, all necessary form work and finishing the top surface rough or smooth as required and directed, providing pockets/openings etc. including vibrating, tampering, curing, rendering and making smooth if required in any position, shape, level and thickness etc. as specified and directed by EIC. The rates include grouting of pockets, supply of material, shuttering, tools & tackles, Reinforcement etc. | CU.M. | 60 | 6002.8 | 360168 |  |  | 6603.08 | 396184.8 | [12 empty] | 0
C.0.02 | Supply and placing in position high strength deformed steel bars reinforcement (conforming to IS: 1786, Grade Fe 415) for RCC work including transporting, straightening, cleaning, de-coiling, cutting & binding to required shapes and length as per details, binding with contractor's own 16 SWG black soft annealed binding wire at every intersection, supplying and placing with proper cover blocks, supports, chairs, overlaps, welding, spacers, fan hooks etc. for all heights and depths etc. complete the work as directed. Note : 1. Rate to include cost of all labour, tools, tackles, equipment, hire charges, supply of all materials such as steel Reinforcement, binding wire and other minor construction materials, testing etc. all bye works and sundry works. | KG | 750 | 66.31 | 49732.5 |  |  | 72.941 | 54705.75 | [12 empty] | 0
C.1.00 | Installations of DRS/DCU/MRS/ Metering Skid / Wall mounted skid |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Receiving, handling, loading, transportation and unloading of owner supplied DRS/MRS/ Metering Skid/ wall mounted skid from Owner's designated stock yards to Contractor's own stock-yards/ work-sites. Proper storing, stacking, identification, providing security and insurance cover for the materials. Supply of cover box for service regulator is in the scope of contractor. Installations of DRS/MRS/ Metering Skid/ service regulator with all associated work at foundation and hooking up with PE pipe line.The scope includes supply of transition fittings and other PE and CS fittings as per requirements and various associated works (including steel welding, if required) to commission DRS/MRS/Metering Skid/wall Mounted skid. Payment towards civil foundation work & structural work for gate and fencing shall be payable as per relevant SOR items. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
C.1.01 | DRS / DCU | Nos | 5 | 27920 | 139600 |  |  | 30712 | 153560 | [10 empty] | 0 |  | 0
C.1.02 | MRS / Metering Skids Providing, fabricating and installation of Metering, regulating system for natural gas supply to various industrial customers with 32mm (1.5") Carbon Steel pipe along with all the fittings having pressure regulation up to 2.0 bar and diaphragm/RPD meter of various range (G-10 to G-25). The installation shall be done as per the Drg no.- 14588-30-05-22 given as annexure. Item includes supply of all the materials such as valves, strainer, reducers or other Fittings and clamps etc required as per the scheme except Meter and Pressure Regulator which shall be supplied by GNGPL. However, installation Meter and Regulator shall also include in the scope of this item. CS pipe shall confirm to ASTM A106 Gr B 150# and fittings shall confirm to ASTM A105, welding Radiography nad testing of pipes & fittings, shall be carried out as per applicable welding code. All the pipes shall be painted with min 02 coat of kennary yellow synthetic paint over a coat of steel primer. The receiving and transportation of free issue material such as Meter and Regulator from GNGPL store to site is in the scope of this item. Note. - The above rates include supply of all materials such as all valves, pipe and fittings etc. No further payment shall be given separately for any supply item. | Nos | 15 | 90000 | 1350000 |  |  | 99000 | 1485000 | [10 empty] | 0 |  | 0
C.1.03 | Installation of Service Regulator with canopy including all fittings with Civil work | Nos | 50 | 6282 | 314100 |  |  | 6910.2 | 345510 | [10 empty] | 0 |  | 0
C.2.00 | Installation of Valve Chambers: |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| All civil works including supply of materials, excavation of pit, piping supports including all PCC, RCC and Brick works for valve pits, sand filling to cover valve body and pits, pedestals with insert plates as required, sealing of pipes in pits, providing cover etc., finishing, clean up and restoration. The work shall be executed as per specification. Also providing water proofing agents internal and external plaster of chamber to avoid water seepage. Refer Drg No 1007- 10-03--19, 20, 21 & 22.) |  |  |  | 0 |  |  | 0 | 0 | [9 empty] | Required Size |  |  | 0
C.2.01 | RCC Valve Chambers- Size (L x W)- 1m x 1m | Nos | 13 | 23034 | 299442 |  |  | 25337.4 | 329386.2 | [9 empty] | 1 | #DIV/0! |  | #DIV/0!
C.2.02 | RCC Valve Chambers- Size (L x W)- 1.5m x 1 m | Nos | 3 | 34202 | 102606 |  |  | 37622.2 | 112866.6 | [9 empty] | 1.5 | #DIV/0! |  | #DIV/0!
C.2.03 | Brick Valve Chambers- Size (L x W)- 1 m x 1 m | Nos | 2 | 17240.6 | 34481.2 |  |  | 18964.66 | 37929.32 |  |  | Factor between RCC and brick | [6 empty] | 1 | #DIV/0! |  | #DIV/0!
C.2.04 | Brick Valve Chambers- Size (L x W)- 1.5m x 1 m | Nos | 2 | 25826 | 51652 |  |  | 28408.6 | 56817.2 |  |  | #DIV/0! | [6 empty] | 1.5 | #DIV/0! |  | #DIV/0!
PART -IV (Marketing) DMA |  |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
D.0.00 | Carrying out the work of obtaining PNG registration in all respect as detailed in Scope of work and Special Conditions of contract and as per directions/instructions of Engineer In charge /Authorized representative including but not limited to following : 1) Enrolment & Registration of PNG Customers as per the given target. 2) Collection of filled up form along with Security Deposit amount (only in the form of cheque/Demand Draft/ Online mode) and relevant documents. 3) Carrying out the work of demand registration, evaluation, facilitation of signing of GSA and collection of security deposit and payment against payment security as detailed in scope of work and special condition of contract of tender document as per requirement and the satisfaction of the EIC for industrial and commercial customers. 4) Carrying out the marketing activities for PNG connection as per directions/instructions of the EIC including but not limited to the following: Printing & Distribution of leaflets & FAQ, Printing & Installation of banners at prime locations, Awareness cum Registration Camp, Audio/Visual Presentations, Organizing Road Shows, etc. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
D.0.01 | Domestic PNG Connections | Nos | 5000 | 181.48 | 907400 |  |  | 199.628 | 998140 | [10 empty] | #DIV/0! |  | #DIV/0!
D.0.02 | Commercial PNG Connections | Nos | 50 | 1326.2 | 66310 |  |  | 1458.82 | 72941 | [10 empty] | 0 |  | 0
PART -V (PENDING MDPE/LMC WORK DONE BY OTHER CONTRACTORS & FABRICATION JOB. |  |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
E.0.00 | LMC SECTION (GI) |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
E.0.01 | Charges for testing & commissioning of GI Riser work done by other contractor 1/2" ,3/4",1" NOTE: It includes fitting, painting, PVC sleeves,Clamping if required is applicable and submission of drawing. | M | 6000 | 35 | 210000 |  |  | 38.5 | 231000 | 35 | [11 empty] | 0
E.1.00 | MDPE SECTION |  |  |  | 0 |  |  | 0 | 0 | 0 | [11 empty] | 0
| Charges for Rectification/Hookup of existinhg networks ( Including all fittings), testing & commissioning MDPE network. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
| Pneumatic testing, purging with nitrogen & Commissioning of already laid MDPE Pipe (PE 100, SDR 11) including supply of manpower, labour (to identify the leak / making the pits), jointing of fittings, its installation and manpower, labour (for making the pits) etc. and submission of final documents (Like: As-built etc) and tapping from main line/charged line is the scope of contractor. The supply of all kind of MDPE fitting including, padestal TF etc is covered under this SOR. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
E.1.01 | Charges for testing & commissioning of MDPE work done by other contractor upto Dia 63 mm | M | 11000 | 85 | 935000 |  |  | 93.5 | 1028500 | 85 | [11 empty] | 0
E.1.02 | Charges for testing & commissioning of MDPE work done by other contractor above Dia 63 mm | M | 11000 | 90 | 990000 |  |  | 99 | 1089000 | 90 | [11 empty] | 0
E.2.00 | Restoration to original conditions of dismantled surface like Asphalted/Bituminous Road, Concrete Pavement, Agra /Kota Stones / Tiles (Chequered/interlocking etc.), Dry Brick Pavement as per the technical specifications attached in the tender after laying of pipeline in Built- Up surface, as per the directions of EIC / Site incharge. Scope includes supply of the approved quality material, testing of materials by third party agencies as per technical specification / CPWD / IRC Standards, submission of the restoration reports, obtaining no objection certificates from the concerned local authorities /land owners / third party inspection agencies designated by land owing agencies and owners. |  |  |  | 0 |  |  | 0 | 0 | [12 empty] | 0
E.2.01 | Restoration of Asphalted/Bituminous Road | RM | 1000 | 805 | 805000 |  | 3000 | 885.5 | 885500 | 805 | From BGL | [10 empty] | 0
E.2.02 | Restoration Of Concrete Pavement,Agra / Kota Stone/Tiles (chequered/ Ointerlocking etc.) | RM | 5000 | 355.98 | 1779900 |  | 13000 | 391.578 | 1957890 | [12 empty] | 0
E.2.03 | Restoration of Plain cement concrete (PCC) | RM | 6000 | 637 | 3822000 |  | 2000 | 700.7 | 4204200 | 637 | [11 empty] | 0
E.2.04 | Restoration of Dry Brick Pavement | RM | 1000 | 251.28 | 251280 |  | 3000 | 276.408 | 276408 | [12 empty] | 0
F.0.00 | MDPE Service Line laying in old Projects / O&M areas
F.1.00 | MDPE Service Line laying in old Projects / O&M areas Includes laying of pipeline (for 20 & 32mm) in all type of surface i.e., Kutcha, metal, concrete (PCC/RCC), bituminous, tiled, brick lined etc. after racking up of hard surface of any type by any methodology. Roads, Pavement, Footpaths etc. shall be made motorable once the pipeline is laid. Supply & installation of GI Sleeve / Half round Concrete sleeve shall be included in laying rates.(Upto 4 Mtr.) For Extra length as other than 4 mtr. are considered in normal laying. ( NOte : Refereed SOR Item Part I Item No PL000.01.01 ) | No's | 500 | 1500 | 750000
G.0.00 | Liasioning with Land Owning Agencies for Permission
G.1.00 | Submission of applications as per approved drawings provided by owner / owner's representative (Initial Route Survey, Preparation of Drawings, measuring and providing details of surface type shall be in scope of Contractor with approval from Owner / Owner's representative), obtaining & submission of demand note, Coordination, Liaisoning, Obtaining written permissions from Land owing agencies like private road/ apartment road, municipal corporations, PWD, NHAI, AAI, Forest Dept., Indian Railways and any other government/ private agencies who maintains the public lands. including liasioning during execution of work and obtaining NOC from the applicable authorities on completion of work. | RM | 35000 | 50 | 1750000
H.0.00 | Barricading to comply with HSSE
H.1.00 | Barricading of the trenches Cautionary Sign Boards and lighting arrangement shall be provided as per tender spec . The rates include barricading of trenches along with sign boards, lighting etc. and maintain the same till the back filling of the trench. Rates will be payable per metre of BARRICADING PROVIDED. If proper barricading is not provided, GNGPL will barricade the trenches at the risks and costs of the CONTRACTOR and will levy penalty of twice the rate per unit for the relevant section of the pipeline apart from other actions as per contract. | RM | 23000 | 100 | 2300000
| Non Destructive Testing (NDT) for regulator inlet piece for I&C Connections per installation |  |  |  | 0 |  | 500 | 0 | 0 | [12 empty] | 0
| Notes: 1) The SOR items would be executed as per the job requirement. 2) The scope as mentioned in the above SOR is of indicative nature only and shall include all activities as detailed in the relevant clauses of the specifications. 3) Any other material & activities not mentioned/covered above, but otherwise required for satisfactory completion/safety of work as defined in tender has to be supplied / done by contractor at no extra cost to owner. 4) Prices quoted in column shall be all inclusive of all taxes / duties (excluding GST) and nothing extra shall be payable by the Owner except for statutory variation in GST. 5) The quantities mentioned in SOR are tentative only and for the purpose of evaluation and may vary as per the actual site condition. 6) The SOR shall be read along with the relevant clauses of tender document |  |  |  | 0 | [16 empty] | 0
Total Cost (Excluding GST) |  |  |  |  | 88438237.7 |  |  |  | 92002061.47
GST @18% |  |  |  |  | 15918882.786 |  |  |  | 16560371.0646
Grand Total (Including GST) |  |  |  |  | 104357120.486 |  |  |  | 108562432.5346
|  |  | Maximum Amount |  | 12000000

## AOP (2) (hidden)
SCHEDULE OF RATES (SOR) RATE CONTRACT FOR MDPE LAYING, ABOVEGROUND GI INSTALLATIONS INCLUDING LAST MILE CONNECTIVITY & DIRECT MARKETING SERVICES AT NORTH GOA-GA Tender No.:
Item NO. |  | Existing Rate | [5 empty] | 10% over head |  | Referance Rate
1 |  | Unit | Quantity | Unit Rate | Amount |  |  |  |  | IGL | BGL | Old LMC/MDPE tender | Purposed | Revised unit rate | Revised Total Amount | [10 empty] | For HDD
PART-I : PE SECTION | [25 empty] | 20% | Calculated Rate |  | Adopted Rate
A | Route survey of allotted areas and Preparation /Submission of detailed route plan for approval by EIC in AutoCAD format. Receiving, handling, loading, transportation and unloading of owner supplied MDPE pipes and other free issue items from GNGPL's designated stock yards to Contractor's own stock-yards/ work-sites. Proper storing, stacking, identification, providing security and insurance cover for the materials. Procurement / Supply and Installation of PE Fittings, PE Valves, Transition Fittings, Warning Mats, HDPE casing Pipes, Half concrete sleeves and all other items required for execution shall also be in Contractor's scope. Liaisoning with Landowning agencies / statutory authorities and obtaining permission from them making trial pits to determine the underground utilities/ services etc., restoration of the abandoned excavation/ trial pits (excavated to depth of 1.5 m or more as per satisfaction to EIC) to original condition, barricading the work area as per the procedures & drawings provided in the tender and as per the directions of EIC / Site-in-charge; uncoiling / stringing of pipes, jointing of the pipe ends/ fittings (Isolation Valve 1/2" & 3/4") / Transition fittings/ valves by qualified personnel, using approved electro fusion techniques as per specification. Installation of PE Valve shall be done as per PNGRB guideline and Instructions of EIC.
Trenching of normal soil / Morrum (red soil)/ Malva / Multiple layer of Bitumen road, hard rock/ boulders using manual/pneumatic chisel and disposal of excess soil/boulders/rock etc. is in the scope of contractor and the same is to be considered by the contractor.
Surveying of route and detours required at the time of execution, preparation of construction drawings showing survey details and submit same to GNGPL/PMC for review/approval.
Submission of applications as per approved drawings provided by owner / owner's representative (Initial Route Survey, Preperation of Drawings, measuring and providing details of surface type shall be in scope of Contractor with approval from Owner / Owner's representative), obtaining & submission of demand note, Coordination, Liaisoning, Obtaining written permissions from Land owing agencies like private road/ apartment road, municipal corporations, PWD, NHAI, AAI, Forest Dept., Indian Railways and any other government/ private agencies who maintains the public lands. including liasioning during execution of work and obtaining NOC from the applicable authorities.
Compliance to T4S, construction safety of MDPE Section-PPE, Continuous hard Barricades along the trenches as per approved drawing in tender, Use of Gum Boots, Hand gloves, Reflective jackets, Hard hats (helmets), Safety shoes, eye and ear safety equipment's, Fire extinguishers and as per the detailed scope of work in tender specifications.
Laying using any method (Open trench & Moling/ HDD) with or without casing; it includes survey of the under ground utilities, execution of the work as per specification (as per trench dimension Drg -attached in tender), including excavation of pits, moling with hole size not exceeding 20% of the the carrier / casing pipe dia. jointing and insertion of the carrier pipe in casing pipe (on case to case basis) and subsequent padding with soft soil, laying of warning mat in open trench only, backfilling, compaction, submission of as built drawing, as graphs as per attached specification and instruction of ElC / Site Engineer of Owner. Includes laying of pipeline in all type of surface including Kutcha, metal, concrete (PCC/RCC), bituminous, tiled, brick lined etc. after raking up of hard surface of any type; Roads, Pavement, Footpaths etc. shall be made motorable once the pipeline is laid.
All service line as required shall be laid within this SOR and no extra payment shall be made for service line in any other SOR line item.
Supply & installation of Gl Sleeves, 2.5" NB x 300 mm length GI pipe Sleeve / Half Round Concrete Sleeves for domestic connections, 3" NB x 300 mm length Gl Sleeve for commercial and industrial installations (as per GI Pipe Sleeve Drg - attached in tender), and 1/2 Round concrete sleeve, Drg- attached in tender) excavation, breaking through any obstructions, insertion of pipe, sealing the annulus, fixing of the sleeves with concrete mix, preparation of pedestal & restoration of excavated pits within the size of pedestal & the same pit with the laying of 20/32 mm dia MDPE pipe as defined in technical specification and instruction of ElC.
Restoration to original conditions of dismantled surface like Asphalted/Bituminous Road, Concrete Pavement, Agra /Kota Stones / Tiles (Chequered/interlocking etc.), Dry Brick Pavement as per the technical specifications attached in the tender after laying of pipeline in Built- Up surface, as per the directions of EIC / Site lncharge. Scope includes supply of the approved quality material, testing of materials by third party agencies as per technical specification / CPWD / IRC Standards, submission of the restoration reports, obtaining no objection certificates from the concern local authorities /land owners / third party inspection agencies designated by land owing agencies and Owner.
Flushing, cleaning ,Pneumatic testing, purging with nitrogen and commissioning as per specification and approved procedures providing all tools and tackles, nitrogen, instruments, manpower and other related accessories including PPE and as per instructions of the Engineer-in charge.
Maintaining the completed pipelines/ installation for any defect, failures during defect liability period.
Handing over the completed works to GNGPL for their operation/ use, returning of all surplus material to GNGPL stores, reconciliation of free issue material area wise and obtaining no objection certificate.
On completion of gas charging of pipelines, preparation and submission of As built drawings, As graph drawings, crossings details, termination, utility graphs and deviation statements with Hard & Soft copy.
Submission of all documents required for contract closure in numbers as mentioned in contract.
GPS Co-ordinate to be taken of laid PE pipeline and GPS instrument to be in Contractors scope.
Laying of MDPE pipeline, with or without casing, in case if existing dedicated trench of approx. size 400mm x 600mm is already provided with removable top cover; Scope includes removal of precast RCC slab covers from channel, laying of pipeline, jointing, testing, sand filling (including supply) refixing top cover of pipe trench.
In case 2 MDPE pipelines are laid in a common trench, SOR rate of higher dia plus 1/3 (0.333) x SOR rate of lower dia will be paid
Note: Supply & Installation of GI Sleeve 1/2 round concrete sleeve(pedastal) & warning mat (Open trench excavation) shall be included in laying of MDPE Pipe.
Any other activities not mentioned / covered explicitly above, but otherwise required for satisfactory completion / operation / safety / statutory / maintenance of the works shall also be covered under the scope of work and has to be completed by Contractor within specified schedule at no extra cost to Owner. All the work shall be executed in accordance with the provision of contract.
A.0.00 | MDPE Pipe line laying in all type of surface, (Katcha surface/ Normal Surface/Hard surface) by Trenching Method
A.0.01 | 20 mm Dia | M | 2000 | 446.72 | 893440 |  |  | 491.392 | 982784 |  |  |  |  | 446.72 | 893440 | TRUE | [9 empty] | 0 | 0 |  | 0
A.0.02 | 32 mm Dia | M | 8848 | 460 | 4070080 | 100 |  | 506 | 4477088 |  |  |  |  | 460 | 4070080 | TRUE
A.0.03 | 63 mm Dia | M | 8500 | 481.62 | 4093770 | 170 |  | 529.782 | 4503147 |  |  |  |  | 481.62 | 4093770 | TRUE | [9 empty] | 34 | 204 |  | 200
A.0.04 | 90 mm Dia | M | 3000 | 558.4 | 1675200 | 60 |  | 614.24 | 1842720 |  |  |  |  | 558.4 | 1675200 | TRUE | [10 empty] | 60 |  | 60
A.0.05 | 125 mm Dia | M | 2000 | 628.2 | 1256400 | 40 |  | 691.02 | 1382040 |  |  |  |  | 628.2 | 1256400 | TRUE | [10 empty] | 40 |  | 40
A.1.00 | MDPE Pipe line laying by HDD Method, with or Without casing (Including supply & installation of HDPE Casing Pipes) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
| Survey of the under ground utilities, submission of HDD profile for approval (excluding road and nala crossings), execution of the work as per the standard procedure attached, including excavation of the pits, Jointing of casing and carrier pipe and insertion of the carrier pipe in casing of dia ranging from 120mm to 180mm for 90 mm & 200mm to 250 mm dia for 125 mm dia MDPE , subsequent sealing, backfilling, compaction, submission of as built graphs, final HDD profiles as per attached specification and the instruction of EIC / Site Engineer of Owner. The other activities are as per SOR Item No. I and as detailed in specification and as per the instructions of the EIC / Site engineer of Owner. The supply of casing pipe shall bein the scope of contractor. The payment shall be made for length of casing pipe laid in HDD, remaining carrier pipe length without casing shall be paid under SOR item no.1 |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
A.1.01 | Laying of 63 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 3000 | 1689.16 | 5067480 | 60 |  | 1858.076 | 5574228 |  |  |  |  | 1689.16 | 5067480 | TRUE | [10 empty] | #REF! |  | #REF!
A.1.02 | Laying of 90 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 6500 | 1700 | 11050000 | 130 |  | 1870 | 12155000 |  |  |  |  | 1700 | 11050000 | TRUE
A.1.03 | Laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata without casing. | M | 1000 | 1731.04 | 1731040 | 20 |  | 1904.144 | 1904144 |  |  |  |  | 1731.04 | 1731040 | TRUE | [10 empty] | #REF! |  | #REF!
[5 empty] | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
A.1.04 | Laying of 63 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2240.58 | 224058 | 2 |  | 2464.638 | 246463.8 |  |  |  |  | 2240.58 | 224058 | TRUE | [10 empty] | #REF! |  | #REF!
A.1.05 | Laying of 90 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2260 | 226000 | 2 |  | 2486 | 248600 |  |  |  |  | 2260 | 226000 | TRUE
A.1.06 | Laying of 125 mm Dia MDPE by HDD method in all type of soil strata including hard rock strata with casing. | M | 100 | 2282.46 | 228246 | 2 |  | 2510.706 | 251070.6 |  |  |  |  | 2282.46 | 228246 | TRUE | [10 empty] | #REF! |  | #REF!
[15 empty] | 0 | TRUE
A.1.07 | MDPE Service Line laying in old Projects / O&M areas | [13 empty] | 0 | TRUE
| MDPE Service Line laying in old Projects / O&M areas Includes laying of pipeline (for 20 & 32mm) in all type of surface i.e., Kutcha, metal, concrete (PCC/RCC), bituminous, tiled, brick lined etc. after racking up of hard surface of any type by any methodology. Roads, Pavement, Footpaths etc. shall be made motorable once the pipeline is laid. Supply & installation of GI Sleeve / Half round Concrete sleeve(pedastal) shall be included in laying rates.(Upto 4 Mtr.) For Extra length as other than 4 mtr. are considered in normal laying. ( NOte : Refereed SOR Item Part I Item No A.0.00 ) | No's | 500 | 1786.88 | 893440 | [5 empty] | 3500 |  |  | 3500 | 1750000 | FALSE | 3500 | bgl
[15 empty] | 0 | TRUE
A.2.00 | Excavation of hard rock |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Trenching of Hard Rock is defined as trench material with a single piece of rock, dimension exceeding 1.0 meter in any direction, which requires cutting only by use of manual/pneumatic chisel/drill or sledge hammer and chisel or removal of same by additional techniques. The disposal of excess rock as per the requirement of authorities. The rates are payable over and above the Laying rates as per relevant SOR item no. - PL000.01.00. |  |  |  | 0 |  | 24000 | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
A.2.01 | Excavation of Hard Rock. | CUM | 500 | 928.34 | 464170 |  |  | 1021.174 | 510587 |  |  |  | 1200 | 1200 | 600000 | FALSE | 1200 | purposed | [8 empty] | #DIV/0! |  | #DIV/0!
[15 empty] | 0 | TRUE
A.3.00 | Fabrication & Installation of Pipeline Markers: |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Supply and Installation of Stone Route Markers, Powder Coated Plate / Pole Markers as per the attached drawings, along the route / along boundary wall, lamp posts including all associated civil works such as excavation and construction in all types of soils, construction of pedestals of RCC and PCC and grouting with concrete, cleaning, supply and application of approved colour and quality of primer and paint, stencil letter cutting of numbers, direction, chainage etc., restoration of area to original condition and performing all works as per drawings, specification and instruction of Engineer-in-Charge. The rates shall include liaison rates with statutory bodies and restoration rates and no separate rates are payable under this SOR. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
A.3.01 | RCC Route Markers as per Drg- attached in tender and as per instruction of EIC and specifications. | Nos | 480 | 369.94 | 177571.2 |  | 160 | 406.934 | 195328.32 |  | 849 |  |  | 849 | 407520 | FALSE | 849 | From BGL | [8 empty] | 0 |  | 0
A.3.02 | Pole markers with foundation as per Drg- attached in tender and instructions of EIC and specification | Nos | 160 | 1535.6 | 245696 |  |  | 1689.16 | 270265.6 |  | 3183 |  |  | 3183 | 509280 | FALSE | 3183 | [9 empty] | #DIV/0! |  | #DIV/0!
A.3.03 | Plate marker as per Drg Drg- attached in tender and as per instruction of EIC and specifications. | Nos | 500 | 209.4 | 104700 |  |  | 230.34 | 115170 |  | 582 |  |  | 582 | 291000 | FALSE | 582 | [9 empty] | #DIV/0! |  | #DIV/0!
PART II : GI / COPPER SECTION |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
B | Supply & Installation of Powder Coated GI Pipe & Fittings |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Assessment of material requirement for installation at site, Order placement and Purchasing of Powder coated Gl Pipes, GI fittings, Copper pipes & fittings, Brass Fittings, Isolation Valves & appliance valves from approved vendors of GNGPL, Scheduling, Planning of material & Forwarding inspection call, getting dispatch clearance, handling, loading, transportation and unloading of these items at respective contractor's store. Receiving, taking over, handling, loading, transportation and unloading of owner supplied above ground fittings such as regulators, meters and free issue items (if any other) as defined in specification from Owner's designated stock yards to Contractor's own stores / work sites, proper storing, stacking, identification, providing security and insurance cover. Preparation and approval of sketches, schedules & execution procedures. Finalising optimum route with consent of customer from transition fitting to cooking oven / appliance and ensuring installations in well ventilated area. Making temporary but stable platforms/ scaffolding/ rope ladders and supply of all other safety devices. Portal entry for new connections - New registration tracking and feasibility survey and its updation as per GNGPL defined TAT; printing of stationary as per approved GNGPL formats required during connections. Follow-up and attend complaints receives from customer regarding delay in new connection & NG conversion (Refer Drg attached in tender) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Installation of GI service pipes & fittings, regulators, Valves etc. including NPT threading, as specified, Drillings of holes through the walls (Brick, RCC), Granite, Marble, Wood Cutting, Glass Cutting with proper heavy duty hammer drill machine, tools & tackles, using proper sealant/ grout material and colours to match the original replacement of the damages during drilling, restoring the area to the original condition, Painting of scratched length of powder coated pipe and fittings after proper surface finish by one coat of approved primer paint and two coats of approved synthetic enamel paint. Restoring the wall surface to original conditions. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Copper tube shall be installed from the downstream of meter up to the isolation valve before the customer appliance as per requirement and the satisfaction of EIC, the contractor to provide all equipment, tools and materials necessary to execute the work in efficient manner by cutting, cleaning, flux application, soldering and lacquering. The work includes supply of tools, tackles and consumables including clamp for fixing the tubes. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Supply & fixing of approved clamps & nylon rawl plugs with SS-304, 2" screws, grout material, suitable thread sealant i.e. Teflon Tape, Joining of transition fitting to above ground service GI pipes, testing, purging and commission of the complete installation. The rates in connections also includes meter installation, tap off rates. The GI installation in already gas charged areas, planning & coordinating with existing consumer's for New tap offs from existing riser with or without tee, testing of these existing risers and commissioning of these connections with newly tapp offs etc.is inclusive. Payment against the commissioning of GI pipe shall be made as per seperate SOR mentioned. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE |  |  | VIJAY SALES CORPORATION PRICE LIST FOR JINDAL STAR W.E.F.: 11/03/2022 | Discount @ 40% | Fittings | Sum | Freight | OHPM |  | Quantity as communicated by PM (Jitender Sir) | Supply Rate | Installation Rate | #VALUE!
B.0.00 | GI Work |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE |  |  | Supply | 40% | 30% |  | 5% | 10% |  | metre |  |  | 0
B.0.01 | Supply & Installation of powder coated 1/2" Gl Riser from TF to lateral isolation valve up to G+4 Apt and Individual kothi/ Bungalow. Refer Drg- attached in tender) | M | 8000 | 537.46 | 4299680 | 15000 |  | 591.206 | 4729648 |  |  |  |  | 537.46 | 4299680 | TRUE |  |  | 264 | 188.5714 |  | 188.5714 | 9.4286 | 18.8571 | 216.8571 | 1.5 | 15325.2857 | 15000 | 30330
B.0.02 | Supply & Installation of powder coated 3/4" Gl Riser from TF to lateral isolation valve above G+4 Apt and Individual kothi/ Bungalow. Refer Drg- attached in tender) | M | 7000 | 698 | 4886000 |  |  | 767.8 | 5374600 |  |  |  |  | 698 | 4886000 | TRUE |  |  | 332 | 237.1429 |  | 237.1429 | 11.8571 | 23.7143 | 272.7143 | 1.5 | 409.0714 | 0 | 410
B.0.03 | Supply & Installation of powder coated 1" Gl Riser from TF to lateral isolation valve above G+4 Apt and Individual kothi/ Bungalow. Refer Drg- attached in tender) | M | 2500 | 837.6 | 2094000 |  |  | 921.36 | 2303400 |  |  |  |  | 837.6 | 2094000 | TRUE |  |  | 499 | 356.4286 |  | 356.4286 | 17.8214 | 35.6429 | 409.8929 | 1.5 | 614.8393 | 0 | 610
B.1.00 | METER INSTALLATION |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
B.1.01 | PNG CONNECTIONS IN PROJECT AREA |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Supply and installation from lateral isolation valve to appliance along with meter installation - The cumulative length of 1/2 "GI within 2 m & Cu within 2m or (GI + Cu) within 4m after lateral isolation valve up to appliance along with installation of meter and all fittings. Additional quantity above 4 Meters (GI + Cu) shall be payable only in case cumulative length exceeds 4 m. Payment against additional length of (GI / Cu) shall be as per item B.0.00 & B.2.00. | Nos | 4000 | 1158.68 | 4634720 | 2000 |  | 1274.548 | 5098192 | 2938.87 |  |  |  | 2938.87 | 11755480 | FALSE | 2938.87 | From IGL | [8 empty] | 2000 |  | 2000
B.1.02 | PNG CONNECTIONS IN O&M AREA (ON EXISTING RISER OR GASIFIDE AREA) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Supply and installation from existing riser to appliance along with meter installation - Supply and installation from lateral isolation valve to appliance along with meter installation and all fittings. The cumulative length of 1/2 "GI within 2 m & Cu within 2m or (GI + Cu) within 4m after lateral isolation valve up to appliance along with installation of meter . Additional quantity above 4 Meters (GI + Cu) shall be payable only in case cumulative length exceeds 4 m. Payment against additional length of (GI / Cu) shall be as per item B.0.00 & B.2.00. | Nos | 3000 | 2773.95 | 8321850 | 1500 |  | 3051.345 | 9154035 | 3498.48 |  |  |  | 3498.48 | 10495440 | FALSE | 3498.48 | [9 empty] | 1500 |  | 1500
B.2.00 | Cu installations for pipes more than 2 m per connection |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
B.2.01 | 12 mm Copper Pipe | M | 3000 | 279.2 | 837600 |  |  | 307.12 | 921360 |  |  |  |  | 279.2 | 837600 | TRUE | [10 empty] | 0 |  | 0
LMC | Note: 1. GI, Cu, brass fittings shall not be counted separately. It shall be measured along with GI & Cu pipe. 2. If Cumulative length of GI & Cu increases specified lengths in connection rate SOR no. B.1.01 & B.1.02, extra piping shall be paid considering installation as done in Flats or bungalows as per SOR item no.: B.0.00 & B.2.00. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
B.3.00 | Testing and conversion of Domestic Appliances in Project/O&M area: |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Conversions of all types of LPG Kitchen appliances(including coocking range) to NG based appliances, Supply & changing of the nozzles / jets and associated controls for domestic & imported appliances with proper tools and tackles. The rates include testing (modification if required) of Kitchen piping from meter to Appliance valve and supply and fixing of one steel reinforced rubber hose (1.5 m) per appliance/stove with clamps. Cleaning and performing minor maintenance, greasing etc. of the appliance and replacement or rectification of regulator. Testing and showing the performance to the customer, signing of joint meter records (JMR) and instructing the customer on use & safety norms, complete as per specifications & to satisfaction of owner / Engineer in Charge. This SOR is applicable for left out NG conversions by other contractor or as per the instructions of EIC. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
B.3.01 | Testing and conversion of Domestic Appliances in Project and O&M area: (NG Conversion per Connection) | Nos | 8000 | 153.56 | 1228480 |  |  | 168.916 | 1351328 | 293 |  |  |  | 293 | 2344000 | FALSE | 293 | From IGL | [8 empty] | 0 |  | 0
B.4.00 | COMMERCIAL/NON DOMESTIC CONNECTION |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
B.4.01 | Installation of gas meter,regulator, supply and installation of meter inlet pipe Welded ( Electrical Resistance Welded (ERW) Galvanized Iron (GI) pipes of Heavy class ). Scope of work under pertaining to Commercial /Non Domestic connections . Scope includes Supply and installation of box / enclosure/Meter Bracket (for Gas meter and regulator ), Strainer & Meter Connector . Supply and installation of safety sign boards as per ‘Technical requirements . This SOR is for meter fixation with riser regulator. | Nos | 50 | 6980 | 349000 |  |  | 7678 | 383900 |  |  |  |  | 6980 | 349000 | TRUE
| Industrial Connection | [13 empty] | 0 | TRUE
| Wall mounted skid Providing, fabricating and installation of Metering, regulating system for natural gas supply to various industrial customers with 32mm & 50mm (1.5" & 2") and as per EIC instruction Carbon Steel pipe along with all the fittings having pressure regulation up to 2.0 bar and diaphragm/RPD meter of various range (G-10 to G-25) and as per EIC instruction. The installation shall be done as per the Drg attached in tender given as annexure. Item includes supply of all the materials such as valves, strainer, reducers or other Fittings and clamps etc required as per the scheme except Meter and Pressure Regulator which shall be supplied by GNGPL. |  | 15 | 90000 | 1350000 | [7 empty] | 90000 | 90000 | 1350000 | TRUE |  | From quotation received from Vendors
[15 empty] | 0 | TRUE
B.5.00 | Core Cutting | [13 empty] | 0 | TRUE
| Breaking of RCC Slab /Wall for installation of GI Pipe and sealing of hole after installation of GI pipe as per instruction of E.I.C | [13 empty] | 0 | TRUE
B.5.01 | 8" thickness | Nos | 100 | 535.5 | 53550 | [6 empty] | 535.5 |  | 535.5 | 53550 | TRUE | 535.5 | From LMC/MDPE old tender
B.5.02 | 6" thickness | Nos | 200 | 357 | 71400 | [6 empty] | 357 |  | 357 | 71400 | TRUE | 357
B.5.03 | 4" thickness | Nos | 400 | 238 | 95200 | [6 empty] | 238 |  | 238 | 95200 | TRUE | 238
[5 empty] | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
PART -III : Civil Works |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
C.0.00 | Equipment Foundation works: (Excavation, Providing and Laying Reinforced Cement Concrete (M-20) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
C.0.01 | Excavation in any plane & dimension including disposal of excavated earth up to any lead in all conditions, backfilling using serviceable earth and disposal of surplus and unserviceable earth. Soil to be levelled and properly compacted complete in all respect as per scope of work, technical specification and directions of EIC. Providing and laying REINFORCED CEMENT CONCRETE OF M-20 Grade (Concrete shall be design mix / nominal mix) with 20mm & down size graded crushed stone aggregates in NON SUSPENDED slabs/pavement slabs including pedestals, ramps etc., laying in alternate panels to required slopes, all necessary form work and finishing the top surface rough or smooth as required and directed, providing pockets/openings etc. including vibrating, tampering, curing, rendering and making smooth if required in any position, shape, level and thickness etc. as specified and directed by EIC. The rates include grouting of pockets, supply of material, shuttering, tools & tackles, Reinforcement etc. | CU.M. | 60 | 6002.8 | 360168 |  |  | 6603.08 | 396184.8 |  |  |  |  | 6002.8 | 360168 | TRUE | [12 empty] | 0
C.0.02 | Supply and placing in position high strength deformed steel bars reinforcement (conforming to IS: 1786, Grade Fe 415) for RCC work including transporting, straightening, cleaning, de-coiling, cutting & binding to required shapes and length as per details, binding with contractor's own 16 SWG black soft annealed binding wire at every intersection, supplying and placing with proper cover blocks, supports, chairs, overlaps, welding, spacers, fan hooks etc. for all heights and depths etc. complete the work as directed. Note : 1. Rate to include cost of all labour, tools, tackles, equipment, hire charges, supply of all materials such as steel Reinforcement, binding wire and other minor construction materials, testing etc. all bye works and sundry works. | KG | 750 | 66.31 | 49732.5 |  |  | 72.941 | 54705.75 |  |  |  |  | 66.31 | 49732.5 | TRUE | [12 empty] | 0
C.1.00 | Installations of DRS/DCU/MRS/ Metering Skid / Wall mounted skid |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Receiving, handling, loading, transportation and unloading of owner supplied DRS/MRS/ Metering Skid/ wall mounted skid from Owner's designated stock yards to Contractor's own stock-yards/ work-sites. Proper storing, stacking, identification, providing security and insurance cover for the materials. Supply of cover box for service regulator is in the scope of contractor. Installations of DRS/MRS/ Metering Skid/ service regulator with all associated work at foundation and hooking up with PE pipe line.The scope includes supply of transition fittings and other PE and CS fittings as per requirements and various associated works (including steel welding, if required) to commission DRS/MRS/Metering Skid/wall Mounted skid. Payment towards civil foundation work & structural work for gate and fencing shall be payable as per relevant SOR items. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
C.1.01 | DRS / DCU | Nos | 5 | 27920 | 139600 |  |  | 30712 | 153560 |  |  |  |  | 27920 | 139600 | TRUE | [10 empty] | 0 |  | 0
C.1.02 | MRS / Metering Skids transportation, fabricating and installation of Metering, regulating system for natural gas supply to various industrial customers with Carbon Steel pipe along with all the fittings having pressure regulation up to 2.0 bar and diaphragm/RPD meter of various range (G-10 to G-25). The installation shall be done as per the Drg attached in tender given as annexure. Item includes supply of all the materials such as valves, strainer, reducers or other Fittings and clamps etc required as per the scheme except Meter and Pressure Regulator which shall be supplied by GNGPL. However, installation Meter and Regulator shall also include in the scope of this item. CS pipe shall confirm to ASTM A106 Gr B 150# and fittings shall confirm to ASTM A105, welding Radiography nad testing of pipes & fittings, shall be carried out as per applicable welding code. All the pipes shall be painted with min 02 coat of kennary yellow synthetic paint over a coat of steel primer. The receiving and transportation of free issue material such as Meter and Regulator from GNGPL store to site is in the scope of this item. Note. - The above rates include supply of all materials such as all valves, pipe and fittings etc. No further payment shall be given separately for any supply item. | Nos | 15 | 43625 | 654375 |  |  | 47987.5 | 719812.5 |  |  |  |  | 43625 | 654375 | TRUE | [10 empty] | 0 |  | 0
C.1.03 | Installation of Service Regulator with canopy including all fittings with Civil work | Nos | 50 | 6282 | 314100 |  |  | 6910.2 | 345510 |  |  |  |  | 6282 | 314100 | TRUE | [10 empty] | 0 |  | 0
C.2.00 | Installation of Valve Chambers: |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| All civil works including supply of materials, excavation of pit, piping supports including all PCC, RCC and Brick works for valve pits, sand filling to cover valve body and pits, pedestals with insert plates as required, sealing of pipes in pits, providing cover etc., finishing, clean up and restoration. The work shall be executed as per specification. Also providing water proofing agents internal and external plaster of chamber to avoid water seepage. Refer Drg No 1007- 10-03--19, 20, 21 & 22.) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [9 empty] | Required Size |  |  | 0
C.2.01 | RCC Valve Chambers- Size (L x W)- 600mm x 800mm | Nos | 13 | 23034 | 299442 |  |  | 25337.4 | 329386.2 |  |  |  |  | 23034 | 299442 | TRUE | [9 empty] | 1 | #REF! |  | #REF!
C.2.02 | RCC Valve Chambers- Size (L x W)- 900mm x 900mm | Nos | 3 | 34202 | 102606 |  |  | 37622.2 | 112866.6 |  |  |  |  | 34202 | 102606 | TRUE | [9 empty] | 1.5 | #REF! |  | #REF!
[15 empty] | 0 | TRUE
| Restoration to original conditions of dismantled surface like Asphalted/Bituminous Road, Concrete Pavement, Agra /Kota Stones / Tiles (Chequered/interlocking etc.), Dry Brick Pavement as per the technical specifications attached in the tender after laying of pipeline in Built- Up surface, as per the directions of EIC / Site incharge. Scope includes supply of the approved quality material, testing of materials by third party agencies as per technical specification / CPWD / IRC Standards, submission of the restoration reports, obtaining no objection certificates from the concerned local authorities /land owners / third party inspection agencies designated by land owing agencies and owners. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE
| Restoration of Asphalted/Bituminous Road | RM | 1000 | 349 | 349000 |  | 3000 | 383.9 | 383900 |  | 805 |  |  | 805 | 805000 | FALSE | 805 | From BGL
| Restoration Of Concrete Pavement,Agra / Kota Stone/Tiles (chequered/ Ointerlocking etc.) | RM | 5000 | 355.98 | 1779900 |  | 13000 | 391.578 | 1957890 |  |  |  |  | 355.98 | 1779900 | TRUE
| Restoration of Plain cement concrete (PCC) | RM | 6000 | 418.8 | 2512800 |  | 2000 | 460.68 | 2764080 |  | 637 |  |  | 637 | 3822000 | FALSE | 637
| Restoration of Dry Brick Pavement | RM | 1000 | 251.28 | 251280 |  | 3000 | 276.408 | 276408 |  |  |  |  | 251.28 | 251280 | TRUE
[15 empty] | 0 | TRUE
PART -IV (Marketing) DMA |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
D.0.00 | Carrying out the work of obtaining PNG registration in all respect as detailed in Scope of work and Special Conditions of contract and as per directions/instructions of Engineer In charge /Authorized representative including but not limited to following : 1) Enrolment & Registration of PNG Customers as per the given target. 2) Collection of filled up form along with Security Deposit amount (only in the form of cheque/Demand Draft/ Online mode) and relevant documents. 3) Carrying out the work of demand registration, evaluation, facilitation of signing of GSA and collection of security deposit and payment against payment security as detailed in scope of work and special condition of contract of tender document as per requirement and the satisfaction of the EIC for industrial and commercial customers. 4) Carrying out the marketing activities for PNG connection as per directions/instructions of the EIC including but not limited to the following: Printing & Distribution of leaflets & FAQ, Printing & Installation of banners at prime locations, Awareness cum Registration Camp, Audio/Visual Presentations, Organizing Road Shows, etc. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
D.0.01 | Domestic PNG Connections | Nos | 5000 | 181.48 | 907400 |  |  | 199.628 | 998140 |  |  |  |  | 181.48 | 907400 | TRUE | [10 empty] | #DIV/0! |  | #DIV/0!
D.0.02 | Commercial PNG Connections | Nos | 50 | 1326.2 | 66310 |  |  | 1458.82 | 72941 |  |  |  |  | 1326.2 | 66310 | TRUE | [10 empty] | 0 |  | 0
PART -V (PENDING MDPE/LMC WORK DONE BY OTHER CONTRACTORS & FABRICATION JOB. |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
E.0.00 | LMC SECTION (GI) |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
E.0.01 | Charges for testing & commissioning of GI Riser work done by other contractor 1/2" ,3/4",1" NOTE: It includes fitting, painting, PVC sleeves,Clamping if required is applicable and submission of drawing. | M | 6000 | 27.92 | 167520 |  |  | 30.712 | 184272 |  |  |  | 35 | 35 | 210000 | FALSE | 35 | [11 empty] | 0
E.1.00 | MDPE SECTION |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | 0 | [11 empty] | 0
| Charges for Rectification/Hookup of existinhg networks ( Including all fittings), testing & commissioning MDPE network. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Pneumatic testing, purging with nitrogen & Commissioning of already laid MDPE Pipe (PE 100, SDR 11) including supply of manpower, labour (to identify the leak / making the pits), jointing of fittings, its installation and manpower, labour (for making the pits) etc. and submission of final documents (Like: As-built etc) and tapping from main line/charged line is the scope of contractor. The supply of all kind of MDPE fitting including, padestal TF etc is covered under this SOR. |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
E.1.01 | Charges for testing & commissioning of MDPE work done by other contractor upto Dia 63 mm | M | 11000 | 55.84 | 614240 |  |  | 61.424 | 675664 |  |  |  | 85 | 85 | 935000 | FALSE | 85 | [11 empty] | 0
E.1.02 | Charges for testing & commissioning of MDPE work done by other contractor above Dia 63 mm | M | 11000 | 62.82 | 691020 |  |  | 69.102 | 760122 |  |  |  | 90 | 90 | 990000 | FALSE | 90 | [11 empty] | 0
F.0.00 | Liasioning with Land Owning Agencies for Permission | [13 empty] | 0 | TRUE
F.1.00 | Submission of applications as per approved drawings provided by owner / owner's representative (Initial Route Survey, Preparation of Drawings, measuring and providing details of surface type shall be in scope of Contractor with approval from Owner / Owner's representative), obtaining & submission of demand note, Coordination, Liaisoning, Obtaining written permissions from Land owing agencies like private road/ apartment road, municipal corporations, PWD, NHAI, AAI, Forest Dept., Indian Railways and any other government/ private agencies who maintains the public lands. including liasioning during execution of work and obtaining NOC from the applicable authorities on completion of work. | RM | 35000 | 50 | 1750000 | [8 empty] | 50 | 1750000 | TRUE
G.0.00 | Barricading to comply with HSSE | [13 empty] | 0 | TRUE
G.1.00 | Hard Barricading of the trenches Cautionary Sign Boards and lighting arrangement shall be provided as per tender spec . The rates include barricading of trenches along with sign boards, lighting, PPE etc. and maintain the same till the back filling of the trench. Rates will be payable per metre of BARRICADING PROVIDED. If proper barricading is not provided, GNGPL will levy penalty of 1.5 times the rate per unit for the relevant section of the pipeline apart from other actions as per contract. | RM | 23000 | 100 | 2300000 | [8 empty] | 100 | 2300000 | TRUE
| Non Destructive Testing (NDT) for regulator inlet piece for I&C Connections per installation |  |  |  | 0 |  | 500 | 0 | 0 | [5 empty] | 0 | TRUE | [12 empty] | 0
| Notes: 1) The SOR items would be executed as per the job requirement. 2) The scope as mentioned in the above SOR is of indicative nature only and shall include all activities as detailed in the relevant clauses of the specifications. 3) Any other material & activities not mentioned/covered above, but otherwise required for satisfactory completion/safety of work as defined in tender has to be supplied / done by contractor at no extra cost to owner. 4) Prices quoted in column shall be all inclusive of all taxes / duties (excluding GST) and nothing extra shall be payable by the Owner except for statutory variation in GST. 5) The quantities mentioned in SOR are tentative only and for the purpose of evaluation and may vary as per the actual site condition. 6) The SOR shall be read along with the relevant clauses of tender document |  |  |  | 0 | [9 empty] | 0 | TRUE | [12 empty] | 0
Total Cost (Excluding GST) |  |  |  |  | 73932264.7 |  |  |  | 74160542.17 | [5 empty] | 88441777.5
GST @18% |  |  |  |  | 13307807.646 |  |  |  | 13348897.5906 | [5 empty] | 15919519.95
Grand Total (Including GST) |  |  |  |  | 87240072.346 |  |  |  | 87509439.7606 | [5 empty] | 104361297.45
|  |  | Maximum Amount |  | 12000000

## Sheet1 (hidden)
As per Old tender
| Qty | Unit Rate | Total
GI 1/2" | 2 | 345.1 | 690.2
AV 1/2" | 1 | 301.07 | 301.07
IV1/2" | 1 | 150 | 150
Copper | 2 | 518.84 | 1037.68
House Pipe & Concersion | 1 |  | 0
Meter | 1 | 95 | 95
Total Material Cost |  |  | 2273.95
Labour Cost | 1 | 500 | 500
Total |  |  | 2773.95
|  | 1263.38 | 1452.887
1510.57

## SOR
Schedule of rate
Tender | HIRING OF AGENCY UNDER RATE CONTRACT FOR PNG METER INSTALLATION, PNG CONVERSION AND DIRECT MARKETING ACTIVITIES IN GASIFIED SOCIETIES OF NORTH GOA GEOGRAPHICAL AREA
Vendor name
Item NO. | Description
|  |  | UNIT | Claim % | Unit Rate | Qty | Value
PART II : GI / COPPER SECTION
A | Supply & Installation of Powder Coated GI Pipe & Fittings
A.0.00 | GI installations for pipes more than 2 m per connection
| 1/2" GI Pipe installation more than 2 meter per connection | After completion of all work in all respects | M | 90% |  | 3956 | 0
|  | After submission of documents and closur of contract | M | 10% |  | 3956 | 0
A.1.00 | METER INSTALLATION
A.1.02 | PNG CONNECTIONS IN O&M AREA (ON EXISTING RISER OR GASIFIDE AREA)
| Supply and installation from existing riser to appliance along with meter installation and cutting of glass if required and as per EIC instruction- Supply and installation from lateral isolation valve to appliance along with meter installation and all fittings. The cumulative length of 1/2 "GI within 2 m & Cu within 2m or (GI + Cu) within 4m after lateral isolation valve up to appliance along with installation of meter . Additional quantity above 4 Meters (GI + Cu) shall be payable only in case cumulative length exceeds 4 m. Payment against additional length of (GI / Cu) shall be as per item B.0.00 & B.2.00. | on completion of meter installation with submission of JMR sheet | Nos | 80% |  | 3956 | 0
|  | On Completion of conversion with all relative work | Nos | 10% |  | 3956 | 0
|  | After submission of documents and closur of contract | Nos | 10% |  | 3956 | 0
A.2.00 | Cu installations for pipes more than 2 m per connection
A.2.01 | 12 mm Copper Pipe | After completion of all work in all respects | M | 90% |  | 3956 | 0
|  | After submission of documents and closur of contract | M | 10% |  | 3956 | 0
LMC | Note: 1. GI, Cu, brass fittings shall not be counted separately. It shall be measured along with GI & Cu pipe. 2. If Cumulative length of GI & Cu increases specified lengths in connection rate SOR no. B.1.01 & B.1.02, extra piping shall be paid considering installation as done in Flats or bungalows as per SOR item no.: B.0.00 & B.2.00.
A.3.00 | Testing and conversion of Domestic Appliances in Project/O&M area:
Conversions of all types of LPG Kitchen appliances(including coocking range) to NG based appliances, Supply & changing of the nozzles / jets/ granite cutting and associated controls for domestic & imported appliances with proper tools and tackles. The rates include testing (modification if required) of Kitchen piping from meter to Appliance valve and supply and fixing of one steel reinforced rubber hose upto (1.5 m) per appliance/stove with clamps. Cleaning and performing minor maintenance, greasing etc. of the appliance and replacement or rectification of regulator. Testing and showing the performance to the customer, signing of joint meter records (JMR) and instructing the customer on use & safety norms, complete as per specifications & to satisfaction of owner / Engineer in Charge. This SOR is applicable for left out NG conversions by other contractor or as per the instructions of EIC.
A.3.01 | Testing and conversion of Domestic Appliances in Project and O&M area: (NG Conversion per Connection) | After completion of all work in all respects | Nos | 90% |  | 5547 | 0
|  | After submission of documents and closur of contract | Nos | 10% |  | 5547 | 0
PART -IV (Marketing) DMA
B.0.00 | Carrying out the work of obtaining PNG registration in all respect as detailed in Scope of work and Special Conditions of contract and as per directions/instructions of Engineer In charge /Authorized representative including but not limited to following : 1) Enrolment & Registration of PNG Customers as per the given target. 2) Collection of filled up form along with Security Deposit amount (only in the form of cheque/Demand Draft/ Online mode) and relevant documents. 3) Carrying out the work of demand registration, evaluation, facilitation of signing of GSA and collection of security deposit and payment against payment security as detailed in scope of work and special condition of contract of tender document as per requirement and the satisfaction of the EIC for industrial and commercial customers. 4) Carrying out the marketing activities for PNG connection as per directions/instructions of the EIC including but not limited to the following: Printing & Distribution of leaflets & FAQ, Printing & Installation of banners at prime locations, Awareness cum Registration Camp, Audio/Visual Presentations, Organizing Road Shows, etc.
B.0.01 | Domestic PNG Connections | After completion of all work in all respects | Nos | 90% |  | 3358 | 0
|  | After submission of documents and closur of contract | Nos | 10% |  | 3358 | 0
Total Cost (Excluding GST) | [6 empty] | 0
GST @18% | [6 empty] | 0
Grand Total (Including GST) | [6 empty] | 0
Note
The SOR shall not be altered, modified, deleted, or changed in any manner whatsoever. Any deviation from the prescribed SOR format may render the bid liable for rejection.
The unit rate quoted by the bidder shall remain the same for completion of the work and final closure of the contract.
Payment shall be released as per the claim percentage (%) specified in the Schedule of Rates (SOR), subject to satisfactory completion of the respective activity/work.
The quoted unit rates shall remain firm and fixed throughout the entire contract period and shall not be subject to any escalation or revision for any reason whatsoever.